## Sheet1
ID | Description
1 | Create a CSVreader to read earthquakes & populations
2 | Create initial use relationships of application modules
3 | Display earthquakes with a given radius of input location
4 | Set up EarthquakeT to accurately represent earthquake data
5 | Set up GeoLoc to accurately represent geographical location data
Sprint 1 | Transform data from .csv files to java objects
6 | Search EarthquakeT within a given radius of input location
7 | Sort EarthquakeT objects based on magnitude using MergeSort & QuickSort
8 | Represent GeoLoc objects using an undirected Graph
9 | Fetch data for a customizable location from the geographical API
10 | Display the average population within radius of a customizable location
11 | Calculate a risk rating using both earthquake and population data
Sprint 2 | Completion of Internal Workings of the application
12 | Make an input form to take user inputs
13 | Configure scrollable lists to display earthquakes for an input location
14 | Add options to filter the displayed list of earthquakes
Sprint 3 | Application with Android graphical user interface
Release 1 | Public version without Advertisements
17 | Inject advertisements using Google AdSense
18 | Change current location automatically according to location detection
Sprint 4 | Location detection & advertisements display
Release 2 | Second version with Advertisements from stakeholders